PRODUCT DEVELOPMENT PLAN

# Owned AI Meeting Assistant Project Plan

A private desktop application for meeting recording transcription summaries decisions and action tracking

| Plan baseline | Initial target | Delivery approach |
| --- | --- | --- |
| Version 1.0 | Linux desktop | Local first and evidence linked |

Recommended direction. Build a Linux-first minimum viable product that reliably captures microphone and system audio, processes recordings locally, and produces editable summaries with timestamped evidence. Delay real-time transcription, cross-platform support, and team collaboration until the core pipeline passes accuracy, privacy, and recovery tests.

Prepared for Jihad Ali Hashim
September 2026
Planning horizon 16 weeks

# 1 Executive overview

The project will create a self-hosted meeting assistant that works independently of a particular meeting platform. It will capture audio at the operating-system level, transcribe speech locally, distinguish speakers where feasible, and generate structured notes without sending confidential meeting content to an external Artificial Intelligence provider.

The first release is intentionally focused on dependable post-meeting processing. A successful release is one that never silently loses a recording, makes generated conclusions traceable to the transcript, and allows a user to correct both transcript and summary before export.

## Product objectives

Capture microphone and system audio from online or in-person meetings.

Create time-aligned, searchable transcripts using a locally operated speech-to-text model.

Generate summaries, decisions, risks, questions, and action items with links to supporting transcript segments.

Keep recordings, transcripts, model execution, and application data under the owner’s control.

Provide a foundation that can later support Windows, live transcription, calendars, and team workspaces.

## Measures of success

| Measure | Minimum release target | How it is verified |
| --- | --- | --- |
| Recording reliability | No lost audio in 20 controlled meetings | Recovery and endurance test suite |
| Processing success | At least 95 percent of valid recordings complete | Automated processing runs |
| Transcript usability | Key statements are understandable and timestamped | Human review across accents and noise |
| Summary grounding | Every decision and action links to evidence | Traceability audit |
| Privacy | No meeting content leaves the device by default | Network and configuration verification |
| Recovery | Interrupted recordings reopen without corruption | Forced shutdown and restart tests |

# 2 Scope and boundaries

## Minimum viable product scope

Ubuntu desktop application with meeting start, pause, resume, stop, and recovery controls.

Microphone-only, system-audio-only, and combined capture modes.

Import of common audio and video files for processing.

Reliable English transcription with timestamps; optional experimental language packs remain outside the core release commitment.

Basic speaker labels such as Speaker 1 and Speaker 2, with manual renaming.

Editable transcript and regenerated summary after corrections.

Summary sections for overview, decisions, action items, questions, risks, and next steps.

Local meeting library, full-text search, tags, and Markdown export.

Explicit recording notice, configurable retention, deletion, and local backup.

## Deferred beyond the first release

| Deferred capability | Reason for deferral | Revisit when |
| --- | --- | --- |
| Live transcription | Raises performance and stability risk | Post-processing is consistently reliable |
| Windows and macOS | Each operating system needs a separate audio layer | Linux workflow and interfaces stabilise |
| Meeting bots | Platform permissions and policy dependencies | A clear customer need is validated |
| Mobile capture | Operating systems restrict other-app audio | Desktop product is established |
| Cloud sync and teams | Expands identity, security, and compliance scope | Single-user security is complete |
| Automatic calendar joining | Not needed to prove core value | Calendar plugin is explicitly prioritised |

## Optional experimental multilingual support

Multilingual support will be delivered as an optional experimental model pack. It must not weaken or delay the supported English workflow, and the interface must clearly label experimental results as potentially less accurate. The first experimental languages are Malayalam, Hindi, and Japanese, including Malayalam-English, Hindi-English, and Japanese-English code-switching.

| Capability | Experimental behaviour | Product rule |
| --- | --- | --- |
| Mixed speech | Detect language at short-segment level | Do not force the complete meeting into English |
| Manglish and Hinglish | Preserve spoken code-switching and English technical terms | Do not silently rewrite meaning |
| Writing system | Offer native script, romanised text, or both | Original transcript remains the evidence record |
| Translation | Optional English interpretation stored separately | Never replace the original transcript |
| Summary language | User selects English, Malayalam, Hindi, or Japanese | Unsupported or uncertain output is visibly marked |
| Installation | Downloadable model pack after application setup | Core installer remains smaller and English works independently |

# 3 Users and primary workflows

## Initial user

The initial user is a privacy-conscious professional who attends online and in-person meetings on Ubuntu and needs reliable notes without uploading company conversations to third-party services. The design must remain understandable to a non-technical user even though deployment and model settings may expose advanced controls.

## Core workflows

Record a meeting: choose audio sources, confirm consent, start recording, monitor levels, and stop safely.

Process a meeting: transcribe, identify speech segments, attempt speaker separation, generate notes, and index the result.

Review evidence: open any generated decision or action item at the supporting timestamp.

Correct results: edit transcript text or speaker names and regenerate only the affected outputs.

Find and export: search meetings, filter by date or tag, and export approved notes.

Recover: reopen an interrupted recording and continue processing from the last safe checkpoint.

# 4 Proposed architecture

| Layer | Responsibility | Initial technology |
| --- | --- | --- |
| Desktop interface | Meeting controls, review, search, settings | Tauri, React, TypeScript, Tailwind CSS |
| Capture service | Microphone and system audio, level monitoring | Rust or native bridge with PipeWire |
| Media pipeline | Chunking, conversion, cleanup, metadata | FFmpeg |
| Transcription | English speech-to-text and timestamps | Faster-Whisper multilingual model |
| Speaker analysis | Who spoke when and manual correction | pyannote.audio or evaluated alternative |
| Summary engine | Structured local generation with evidence rules | Ollama and a quantised 3B to 4B model |
| Experimental language pack | Malayalam, Hindi, Japanese, and code-switching | Optional downloadable models and configuration |
| Application service | Jobs, validation, exports, recovery | Python with FastAPI |
| Persistence | Meetings, segments, jobs, actions, settings | SQLite and encrypted file storage |
| Search | Transcript and metadata retrieval | SQLite full-text search |

## Key architectural rules

Audio is written in recoverable chunks rather than held only in memory.

Each processing step is an idempotent job that can safely be retried.

Original transcript segments remain separate from user corrections and generated interpretations.

Generated facts must carry source segment identifiers and timestamps.

A local-only mode is the default; external services require an explicit future opt-in.

Models and engines sit behind interfaces so they can be replaced without rewriting the application.

## Local model and token strategy

The supported default is fully local processing, so model tokens create no usage charge. Token volume still affects processing time and memory. A typical one-hour meeting is expected to produce roughly 9,000 to 14,000 English transcript tokens and potentially 12,000 to 25,000 tokens when several scripts are mixed. Chunk analysis and the final synthesis may process approximately 15,000 to 40,000 tokens in total, depending on speech rate and language mix.

Split transcripts into five to ten minute or topic-based segments and retain structured facts with source timestamps.

Answer later questions by retrieving relevant segments instead of resending the complete transcript.

Ship the application separately from models; offer Lite, Balanced, and Accuracy model packs.

Start with prompting, schemas, glossary support, and constrained output; consider lightweight fine-tuning only after a consented benchmark dataset exists.

Preserve replaceable model interfaces so transcription and summarisation models can be upgraded without changing meeting data.

# 5 Delivery roadmap

The plan assumes one primary developer using Artificial Intelligence-assisted development, with the owner acting as product owner and Quality Assurance lead. The dates are effort ranges rather than contractual commitments.

| Phase | Weeks | Primary outcome | Exit gate |
| --- | --- | --- | --- |
| 0 Discovery | 1 | Validated audio and privacy assumptions | Capture spike works on target Ubuntu device |
| 1 Foundation | 2 to 3 | Application shell, storage, job framework | Meeting lifecycle persists and recovers |
| 2 Recording | 4 to 5 | Reliable source selection and chunked capture | 20 recording scenarios pass |
| 3 Transcription | 6 to 7 | Supported English transcript with timestamps | English benchmark accepted |
| 4 Intelligence | 8 to 10 | Evidence-linked summary and actions | Unsupported claims are rejected or flagged |
| 5 Product experience | 11 to 12 | Review, edit, search, export | End-to-end acceptance scenarios pass |
| 6 Hardening | 13 to 14 | Security, recovery, performance, packaging | Release candidate meets quality gates |
| 7 Pilot | 15 to 16 | Real-meeting validation and release decision | Pilot findings resolved or accepted |

## Phase 0 Discovery and feasibility

Confirm the target Ubuntu, PipeWire or PulseAudio configuration, microphone, headset, and meeting applications.

Build an audio-capture spike and verify separate and mixed tracks.

Benchmark two transcription model sizes against English, Indian accents, background noise, and domain terminology.

Run a separate experimental benchmark for Malayalam, Hindi, Japanese, Manglish, Hinglish, and Japanese-English code-switching without making it a core release gate.

Evaluate speaker separation licensing, download requirements, speed, and accuracy.

Record privacy decisions, retention defaults, consent experience, and company-policy constraints.

Deliverables: feasibility report, benchmark dataset, architecture decision records, prioritised product backlog, and confirmed release criteria.

## Phases 1 to 3 Foundation recording and transcription

Create the repository, coding standards, automated checks, application shell, database migrations, and job state machine.

Implement safe recording with audio meters, device changes, pause and resume, chunk manifests, and crash recovery.

Add file import, audio normalisation, voice activity detection, transcription, timestamps, progress, cancellation, and retry.

Measure processing time, central processing unit and memory consumption, temperature, and transcript usability on the target device.

## Phases 4 to 5 Intelligence and product experience

Define a strict summary schema covering overview, topics, decisions, actions, questions, risks, and next steps.

Require evidence references and represent unknown owners or dates as not specified.

Implement transcript editing, speaker renaming, selective regeneration, search, filters, and exports.

Add meeting templates such as daily stand-up, sprint review, interview, and general discussion.

## Phases 6 to 7 Hardening and pilot

Complete security review, metadata deletion, retention enforcement, backups, restore, and model integrity checks.

Run endurance, interruption, low-disk, device-disconnect, silence, cross-talk, and corrupted-file tests.

Package an installable Ubuntu build with first-run model setup and diagnostics.

Use the release candidate in at least ten consented real meetings and classify every defect and summary correction.

# 6 Work breakdown and backlog

| Epic | Must have stories for first release |
| --- | --- |
| Meeting management | Create, rename, tag, archive, delete, and reopen a meeting |
| Audio capture | Choose sources, view levels, pause, resume, stop, and recover chunks |
| Processing | Queue, monitor, cancel, retry, and resume transcription and analysis |
| Transcript | View timestamps, edit text, rename speakers, and navigate to audio |
| Summary | Generate structured sections, cite evidence, edit, approve, and regenerate |
| Search | Search transcript text and filter by date, participant label, tag, or status |
| Export | Export approved transcript and notes to Markdown and plain text |
| Settings | Choose models, language, storage location, retention, and privacy mode |
| Operations | View diagnostics, storage use, model status, and job errors |

# 7 Quality assurance strategy

Quality assurance starts with measurable fixtures rather than waiting for the user interface. The supported release corpus must cover clean English, Indian accents, technical terms, multiple speakers, interruptions, silence, echo, and poor microphones. A separate experimental corpus will cover Malayalam, Hindi, Japanese, Manglish, Hinglish, and Japanese-English code-switching; failures in that corpus do not block the English release but must remain visible and measured.

| Test level | Coverage |
| --- | --- |
| Unit | Job states, schemas, evidence mapping, retention rules, export transformations |
| Component | Capture, media conversion, transcription adapters, model adapters, database |
| Integration | Recording to transcript, transcript to summary, correction to regeneration |
| System | Real meeting applications, devices, long sessions, restart and low-resource behaviour |
| Security | Local network activity, permissions, deletion, logs, secrets, malicious imported files |
| Artificial Intelligence evaluation | Transcript errors, missed decisions, invented actions, wrong owners, evidence validity |
| Usability | Start-recording clarity, consent visibility, correction effort, export comprehension |

## Release quality gates

No open critical or high-severity defect affecting recording integrity, privacy, or deletion.

All generated decisions and actions either cite a valid transcript segment or are visibly marked uncertain.

A two-hour meeting records and processes without unbounded memory growth.

Forced application termination preserves completed audio chunks and offers recovery on restart.

No outbound meeting-content traffic occurs in local-only mode.

Installation, model setup, backup, restore, and uninstall instructions pass on a clean Ubuntu environment.

## Experimental multilingual evaluation gates

The feature is disabled by default or clearly labelled Experimental before use.

The transcript preserves detected languages and does not automatically translate the evidence record into English.

Native-script and romanised display options never overwrite the original transcript.

Language switching, names, dates, owners, numbers, and technical terms are evaluated separately.

Low-confidence segments are visibly marked and can be reprocessed or corrected.

No accuracy claim is published until each language and mixed-language scenario passes a recorded benchmark.

# 8 Privacy security and responsible use

Show an unambiguous recording state and require the user to confirm that participant consent has been obtained.

Store content locally by default and document every optional network connection.

Encrypt sensitive content at rest where practical, with keys protected by the operating system credential store.

Exclude transcript content from diagnostic logs and crash reports.

Offer retention limits, permanent deletion, and a clear explanation of what each deletion removes.

Treat summaries as drafts requiring review; never present generated notes as a legally authoritative record.

Review model and dependency licences before distribution or commercial use.

# 9 Risks and mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| System audio cannot be captured in a configuration | High | Discovery spike, diagnostics, separate-source fallback, setup guide |
| Central processing unit processing is too slow | High | Quantised models, queued post-processing, configurable model sizes |
| Speaker labels are wrong | Medium | Confidence indicators, manual rename and merge, never infer identity silently |
| Summary invents details | High | Schema validation, evidence requirement, uncertainty states, human approval |
| Recording is interrupted | High | Chunked writes, manifests, periodic flush, recovery tests |
| Storage fills during a meeting | High | Preflight estimate, live threshold warnings, graceful stop |
| Model or licence blocks distribution | High | Licence register and replaceable model adapters |
| Company policy forbids recording | High | Consent flow, policy warning, user-controlled deployment |
| Scope grows before validation | Medium | Phase exit gates and explicit deferred backlog |

# 10 Governance and project operation

## Roles

| Role | Responsibility |
| --- | --- |
| Product owner | Priorities, privacy decisions, acceptance, pilot approval |
| Technical lead | Architecture, interfaces, code quality, delivery decisions |
| Quality Assurance lead | Test strategy, fixtures, evidence, release gates, defect triage |
| Security reviewer | Threat review, data flows, dependencies, packaging and deletion |
| Pilot users | Consented usage, corrections, usability feedback and defect reports |

## Working rhythm

Maintain a prioritised backlog with acceptance criteria for every story.

Work in one-week iterations and demonstrate a usable vertical slice each week.

Record important architectural and privacy choices as short decision records.

Run automated checks on every change and a complete acceptance suite before a release candidate.

Review scope, risks, benchmark results, and confidence at the end of each phase.

## Definition of done

A feature is done only when its acceptance criteria pass; error and recovery paths are covered; privacy behaviour is documented; automated tests exist at the appropriate level; the interface is keyboard usable; logs are safe; and user-facing instructions are updated.

# 11 Immediate next steps

1.  Approve the minimum viable product scope and explicitly accept the deferred feature list.

2.  Choose a working product name and repository location.

3.  Confirm the primary Ubuntu version, audio server, headset, and meeting applications for the feasibility spike.

4.  Collect or create a consented 30 to 60 minute evaluation audio set representing actual accents, languages, and meeting conditions.

5.  Run Phase 0 and decide the transcription model, speaker strategy, summary model, and realistic processing targets from measured results.

6.  Convert the approved plan into epics, user stories, acceptance criteria, and the first one-week iteration backlog.

## First iteration objective

By the end of the first working week, a user should be able to select a microphone and system-audio source, record a ten-minute meeting into recoverable chunks, stop safely, and play back both captured tracks. This proves the most platform-sensitive part before investment in transcription or summarisation.

# 12 Assumptions requiring confirmation

| Assumption | Current planning position |
| --- | --- |
| Primary operating system | Ubuntu Linux first |
| Primary deployment | Single-user desktop application |
| Privacy mode | Fully local by default |
| Processing style | High-quality post-meeting processing before live transcription |
| Supported language | English first, including Indian accents |
| Experimental languages | Optional Malayalam, Hindi, Japanese, Manglish, Hinglish, and Japanese-English pack |
| Transcript policy | Preserve original mixed-language text; translation is optional and separate |
| Model delivery | Core application plus optional downloadable Lite, Balanced, and Accuracy packs |
| Distribution | Personal/internal use first; commercial packaging assessed later |
| Hardware | Central processing unit-only operation must remain usable |
| Meeting consent | The user is responsible for obtaining consent and following policy |